## Time lines mile stones
Invention | [6 empty] | Manufacturing
sno | Road Map- Ideas to Invention systematic approach as per flow chart | time lines | Mile stones |  |  |  | sno | Actual inventive product manufcaturing plan | time lines | Mile stones
|  |  | 25% | 50% | 75% | 100% |  |  |  | 25% | 50% | 75% | 100%
1 | Pool up ideas & store in idea bank of web space | 2015-01-01 |  |  |  |  | 24 | start working on invention stage by stage | 2015-04-06
2 | sort them on month wise | 2015-01-01 |  |  |  |  | 1 | preparation of list of materials / equipment’s required with specification standards | 2015-04-06
3 | Initial prioritizing ideas - tool box from your web space | 2015-01-07 |  |  |  |  | 2 | Enquired with suppliers about the delivery lead time for all the materials | 2015-04-07
4 | Patent search | 2015-01-07 |  |  |  |  | 3 | List Separately short lead time & Long lead time items | 2015-04-08
5 | weightage analyse ideas | 2015-01-15 |  |  |  |  | 4 | Place order for long lead time items first | 2015-04-09
6 | Force field analyse ideas | 2015-01-20 |  |  |  |  | 5 | Place order for short lead time items latter | 2015-04-09
7 | Do a market research | 2015-01-30 |  |  |  |  | 6 | Manufacturing rest of items through proto makers | 2015-05-10
8 | Finalse 1st idea for invention & give a tittle | 2015-02-01 |  |  |  |  | 7 | Receipt of all items | 2015-05-15
9 | complete data collection | 2015-02-10 |  |  |  |  | 8 | Inspection compliance to specification requirements | 2015-05-15
10 | Decide what are all the fields you need mentors | 2015-02-15 |  |  |  |  | 9 | Readiness of tools & tackles ready to carry out assembling | 2015-05-15
11 | Establish contacts with mentors | 2015-02-25 |  |  |  |  | 10 | completion of final assembly | 2015-05-30
12 | Do a SWOT analysis | 2015-02-28 |  |  |  |  | 29 | Test for complaince final stage | 2015-06-05
13 | Do a Mind mapping | 2015-03-01
14 | Make a flow chart | 2015-03-05
15 | Complete writing technical write up / thesis | 2015-03-10
16 | Prepare detailed drawings,specification standards | 2015-03-10
17 | Apply provisonal IP filing | 2015-03-15
18 | Prepare budget | 2015-03-15
19 | Establish contact with investors if beyond your budget | 2015-03-20
20 | Establish contact with proto makers on need base | 2015-03-25
21 | Prepare action plan with mile stones & dead lines | 2015-03-27
22 | Analyse in to number of elements | 2015-03-30
23 | Prepare check list for every stage | 2015-04-05
24 | start working on invention stage by stage | 2015-04-06
25 | Over come set back using cause & effect tools | 2015-04-15
26 | Test for complaince stage vice | 2015-05-15
27 | Incase of problem do a root cause analysis | 2015-05-17
28 | Successful completion of proto type | 2015-05-25
29 | Test for complaince final stage | 2015-06-05
30 | File complete specification IP | 2015-06-10
31 | Establish contact with companies / open invention for TOT or licensing | 2015-06-20
32 | Initiate actions to start the business | 2015-06-30